## 📋 Overview
🚀 6-MONTH AWS DATA ENGINEER TRANSITION PLAN — ₹30 LPA TARGET
From Basics → Advanced ¦ India Mid-Level AWS Data Engineer
Month | Focus Area | Key Topics | Hours/Week | Weekly Goal | Status
Month 1 (Wk 1-4) | Foundations | Python Basics, SQL Fundamentals, Linux, Git, AWS IAM & S3 | 15-20 hrs | Run Python ETL script + Basic SQL queries | ⬜ Not Started
Month 2 (Wk 5-8) | AWS Core Services | AWS Glue, Lambda, EC2, VPC, CloudWatch, EventBridge | 15-20 hrs | Build Glue crawler + Lambda trigger pipeline | ⬜ Not Started
Month 3 (Wk 9-12) | Data Engineering Deep Dive | Redshift, Data Lake concepts, ETL vs ELT, Star Schema | 20 hrs | End-to-end ETL pipeline in AWS | ⬜ Not Started
Month 4 (Wk 13-16) | Big Data & PySpark | Spark, PySpark, Partitioning, Data Skew, Performance tuning | 20 hrs | PySpark job on S3 data with optimization | ⬜ Not Started
Month 5 (Wk 17-20) | Advanced AWS + Streaming | Kinesis, Step Functions, CDC, Schema Evolution, Advanced SQL | 20 hrs | Streaming pipeline with Kinesis + monitoring | ⬜ Not Started
Month 6 (Wk 21-24) | Interview Prep & Projects | Mock interviews, system design, portfolio projects, concepts | 20-25 hrs | Complete 2 capstone projects + 50 mock Qs | ⬜ Not Started
📊 SKILLS PROGRESS TRACKER
Skill Area | Current Level | Target Level | % Complete | Key Resources | Notes
Python | Beginner | Intermediate | 0% | Python.org, Real Python
SQL | Basic | Advanced | 0% | Mode Analytics, LeetCode
AWS Fundamentals | None | Intermediate | 0% | AWS Free Tier, Tutorials Dojo
AWS Glue | None | Intermediate | 0% | AWS Docs, YouTube
Amazon Redshift | None | Intermediate | 0% | AWS Docs, Redshift guide
PySpark | None | Basic-Intermediate | 0% | Databricks Academy, PySpark docs
Data Engineering Concepts | Basic | Strong | 0% | Fundamentals of DE book
Git & Linux | Basic | Comfortable | 0% | GitHub, Linux journey
Streaming / Kinesis | None | Basic | 0% | AWS Kinesis docs
System Design | None | Interview-ready | 0% | Educative.io, YouTube

## 📅 Month 1 - Foundations
📅 MONTH 1: PYTHON • SQL • LINUX • GIT • AWS BASICS
📌 WEEK 1 — Python Basics — Variables, Data Types, Control Flow
🎯 Weekly Goal: Write a Python script that reads a CSV and prints summary stats
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 1 (Mon) | Python Setup | Install Python, VS Code, pip. Variables, data types (int, str, list, dict) | Print name, age, skills list. Run first .py file | Python.org docs | ⬜
Day 2 (Tue) | Control Flow | If/else, for loops, while loops, range(), break/continue | FizzBuzz problem. Loop through a list of numbers | W3Schools Python | ⬜
Day 3 (Wed) | Functions | def, return, *args, **kwargs, default params, scope | Write 5 functions: add, greet, find_max, reverse_str, is_palindrome | Real Python | ⬜
Day 4 (Thu) | File Handling | open(), read/write CSV with csv module. Exception handling try/except | Read employees.csv, filter salary > 50000, write to new file | Python docs | ⬜
Day 5 (Fri) | Python Collections | Lists, dicts, sets, tuples. List comprehensions. Dict operations | Count word frequency in a string using dict. Sort dict by value | Real Python | ⬜
Day 6 (Sat) | Pandas Intro | pip install pandas. read_csv, head, info, describe, shape | Load any CSV dataset. Print first 10 rows, column names, data types | Pandas docs | ⬜
Day 7 (Sun) | Review + Practice | Review week 1. LeetCode easy Python problems (2-3) | Solve: Two Sum, Valid Parentheses on LeetCode using Python | LeetCode | ⬜
📝 WEEKLY ASSIGNMENT: Write a Python script that reads a CSV and prints summary stats
📌 WEEK 2 — Pandas + SQL Basics
🎯 Weekly Goal: ETL script using Pandas + write 10 SQL queries on sample DB
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 8 (Mon) | Pandas ETL | DataFrame operations: filter, groupby, merge, fillna, dropna, apply | Load sales data CSV. Group by region, sum revenue, save to new CSV | Kaggle datasets | ⬜
Day 9 (Tue) | SQL Basics | SELECT, WHERE, ORDER BY, LIMIT, DISTINCT, aliases. Install DBeaver + SQLite | Write 10 SELECT queries on sample DB. Filter products by price | SQLZoo, W3Schools SQL | ⬜
Day 10 (Wed) | SQL JOINs | INNER, LEFT, RIGHT, FULL OUTER JOIN. When to use each join type | Join customers + orders tables. Find customers with no orders (LEFT) | Mode Analytics SQL | ⬜
Day 11 (Thu) | SQL Aggregations | GROUP BY, HAVING, COUNT, SUM, AVG, MIN, MAX. CASE WHEN | Monthly revenue by category. Products with avg rating > 4. CASE | SQLZoo | ⬜
Day 12 (Fri) | SQL Subqueries + CTE | Subqueries in WHERE/FROM. WITH clause CTEs. Nested queries | Top 3 customers by spend using CTE. Subquery: employees above dept avg | Mode Analytics | ⬜
Day 13 (Sat) | Python + DB Connect | sqlite3 module, cursor, execute, fetchall. Connect Python to SQLite | Python script to INSERT 100 rows and SELECT filtered data from SQLite | Python sqlite3 docs | ⬜
Day 14 (Sun) | Review + Mini Project | Combine Pandas + SQL. Review week concepts | Load CSV → clean with Pandas → store in SQLite → query with Python | Your own project | ⬜
📝 WEEKLY ASSIGNMENT: ETL script using Pandas + write 10 SQL queries on sample DB
📌 WEEK 3 — Linux, Git & AWS Setup
🎯 Weekly Goal: Setup AWS Free Tier + create S3 bucket via CLI and console
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 15 (Mon) | Linux Basics | ls, cd, pwd, mkdir, rm, cp, mv, cat, grep, chmod, sudo, pipes ¦ | Navigate file system. Create folder structure. Search text with grep | Linux Journey (linuxjourney.com) | ⬜
Day 16 (Tue) | Linux + Shell | bash scripts, echo, variables, $PATH, environment variables, cron | Write bash script: backup files, list .py files, print current date | Linux Journey | ⬜
Day 17 (Wed) | Git Basics | git init, add, commit, push, pull, clone, status, log, .gitignore | Create GitHub repo. Commit Python ETL project from Week 1-2 | GitHub docs | ⬜
Day 18 (Thu) | Git Branching | git branch, checkout, merge, rebase, pull requests, conflict resolve | Create feature branch. Add new function. Merge to main via PR | GitHub Learning Lab | ⬜
Day 19 (Fri) | AWS Intro + IAM | AWS Free Tier signup. IAM: users, groups, roles, policies, MFA | Create IAM user with S3 read-only policy. Generate access keys | AWS Console + AWS docs | ⬜
Day 20 (Sat) | AWS S3 Console | S3 buckets: create, upload, download, permissions, versioning, lifecycle | Create bucket. Upload CSV files. Enable versioning. Set lifecycle to IA after 30 days | AWS S3 docs | ⬜
Day 21 (Sun) | AWS CLI Setup | Install AWS CLI. aws configure. aws s3 ls, cp, sync commands | CLI: create bucket, sync local folder to S3, list objects, delete object | AWS CLI User Guide | ⬜
📝 WEEKLY ASSIGNMENT: Setup AWS Free Tier + create S3 bucket via CLI and console
📌 WEEK 4 — AWS S3 Deep Dive + Python Integration
🎯 Weekly Goal: Python script that reads/writes to S3 using boto3
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 22 (Mon) | S3 Advanced | S3 storage classes, partitioned data (year/month/day), naming conventions | Design partition structure for order data. Upload sample partitioned CSVs | AWS S3 Best Practices | ⬜
Day 23 (Tue) | boto3 Basics | pip install boto3. s3.put_object, get_object, list_objects, delete_object | Upload file to S3 with boto3. Download and read it back in Python | boto3 docs | ⬜
Day 24 (Wed) | Python ETL to S3 | Read CSV → transform with Pandas → upload processed file to S3 | Full ETL: read raw CSV, clean nulls, add date column, save to S3 as parquet | boto3 + pandas docs | ⬜
Day 25 (Thu) | Encryption + Security | S3 bucket policies, ACL, SSE-S3, SSE-KMS. Cross-account access basics | Enable default encryption on S3 bucket. Add bucket policy for read-only | AWS S3 security docs | ⬜
Day 26 (Fri) | SQL Window Functions | ROW_NUMBER, RANK, DENSE_RANK, LAG, LEAD, PARTITION BY, OVER() | Rank customers by spend per region. Running total of daily sales | Mode Analytics, StrataScratch | ⬜
Day 27 (Sat) | SQL Performance | EXPLAIN, query plans, indexing basics, avoid SELECT *, filter early | Analyze slow query with EXPLAIN. Add index on frequently filtered column | Use The Index Luke | ⬜
Day 28 (Sun) | Month 1 Project | Build complete Month 1 capstone + push to GitHub | Python ETL: read data → clean → transform → save to S3 partitioned folders | GitHub | ⬜
📝 WEEKLY ASSIGNMENT: Python script that reads/writes to S3 using boto3

## 📅 Month 2 - AWS Services
📅 MONTH 2: GLUE • LAMBDA • EVENTBRIDGE • REDSHIFT • CLOUDWATCH
📌 WEEK 5 — AWS Glue — Crawlers & Data Catalog
🎯 Weekly Goal: Create Glue crawler that auto-discovers S3 CSV data and catalogs it
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 29 (Mon) | AWS Glue Intro | What is Glue? Serverless ETL. Data Catalog concept. Glue vs EMR | Read AWS Glue developer guide overview. Draw Glue architecture diagram | AWS Glue docs | ⬜
Day 30 (Tue) | Glue Crawler | Create crawler: IAM role, data store (S3), schedule, database | Create Glue crawler on your S3 CSV data. Run it. View table in Data Catalog | AWS Console + Glue docs | ⬜
Day 31 (Wed) | Data Catalog | Glue Data Catalog: databases, tables, partitions, schema detection | Query cataloged table using Athena. Check auto-detected schema | AWS Glue + Athena docs | ⬜
Day 32 (Thu) | Glue ETL Job (Spark) | Glue job: DynamicFrame, ApplyMapping, write to S3. Glue Studio visual | Create Glue job to read CSV from S3, rename columns, write as Parquet | AWS Glue Studio | ⬜
Day 33 (Fri) | Glue Job Advanced | Job bookmarks, job parameters, Glue triggers, partitioning output | Modify job to partition output by year/month. Enable job bookmark | AWS Glue docs | ⬜
Day 34 (Sat) | Athena Queries | Amazon Athena: query S3 data with SQL. Partitioning for cost savings | Query Parquet files with Athena. Use partition pruning. Check data scanned | AWS Athena docs | ⬜
Day 35 (Sun) | Review + Practice | Review Glue concepts. Draw full Glue pipeline flow | Document your Glue pipeline. Push Glue PySpark script to GitHub | GitHub | ⬜
📝 WEEKLY ASSIGNMENT: Create Glue crawler that auto-discovers S3 CSV data and catalogs it
📌 WEEK 6 — AWS Lambda + EventBridge Automation
🎯 Weekly Goal: Build event-driven pipeline: S3 upload → Lambda → trigger Glue job
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 36 (Mon) | Lambda Basics | AWS Lambda: event-driven, handler function, runtime (Python3.x), timeout | Create Hello World Lambda in Python. Test with test event in console | AWS Lambda docs | ⬜
Day 37 (Tue) | Lambda + S3 Trigger | S3 event notifications → Lambda. Event object structure. Read S3 key | Lambda triggered on S3 upload: print bucket name and file key to CloudWatch | AWS Lambda + S3 docs | ⬜
Day 38 (Wed) | Lambda + Glue | Start Glue job from Lambda using boto3. Pass parameters. Check job status | Lambda: when CSV uploaded to S3, start Glue ETL job via boto3 | boto3 Glue client docs | ⬜
Day 39 (Thu) | EventBridge Rules | Amazon EventBridge: rules, event patterns, targets, cron schedules | Create EventBridge rule to trigger Lambda every day at 8 AM IST | AWS EventBridge docs | ⬜
Day 40 (Fri) | Lambda Layers + Env Vars | Lambda layers for shared libraries. Environment variables. Lambda limits | Add pandas layer to Lambda. Store S3 bucket name as env variable | AWS Lambda layers docs | ⬜
Day 41 (Sat) | IAM Deep Dive | IAM policies JSON: Effect, Action, Resource. Inline vs managed policies | Write custom IAM policy for Lambda to read S3 + start Glue. Least privilege | AWS IAM docs + policy simulator | ⬜
Day 42 (Sun) | Pipeline Project | Combine: S3 → Lambda → Glue → Athena query | Build end-to-end: upload CSV → Lambda detects → starts Glue → Athena query | Your AWS account | ⬜
📝 WEEKLY ASSIGNMENT: Build event-driven pipeline: S3 upload → Lambda → trigger Glue job
📌 WEEK 7 — Amazon Redshift — Data Warehouse
🎯 Weekly Goal: Load S3 data into Redshift, run analytical queries, explain distribution
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 43 (Mon) | Redshift Intro | What is Redshift? Columnar storage, MPP architecture, nodes vs leader node | Read Redshift architecture guide. Compare Redshift vs RDS vs S3+Athena | AWS Redshift docs | ⬜
Day 44 (Tue) | Redshift Setup | Create Redshift cluster (dc2.large, free trial). Connect with DBeaver/SQL client | Create cluster. Connect DBeaver. Run: SELECT version(). Create schema | AWS Redshift getting started | ⬜
Day 45 (Wed) | Table Design | CREATE TABLE, data types, DISTKEY, SORTKEY, ENCODE compression | Create orders table with DISTKEY(customer_id) and SORTKEY(order_date) | Redshift table design guide | ⬜
Day 46 (Thu) | COPY Command | COPY from S3 to Redshift. IAM role, manifest files, CSV vs Parquet load | Load S3 Parquet file into Redshift using COPY. Check STL_LOAD_ERRORS | AWS Redshift COPY docs | ⬜
Day 47 (Fri) | Distribution Styles | EVEN, KEY, ALL distribution. When to use each. Join performance | Create 3 tables with different distributions. Analyze EXPLAIN plan for join | Redshift dist style docs | ⬜
Day 48 (Sat) | Sort Keys + Perf | Compound vs interleaved sort keys. VACUUM, ANALYZE commands | Run EXPLAIN on 3 queries. Add sort key. Re-run EXPLAIN. See improvement | Redshift perf tuning guide | ⬜
Day 49 (Sun) | Redshift Queries | Window functions in Redshift, analytical SQL, LISTAGG, WLM queues | Run 10 analytical queries: rankings, running totals, cohort analysis | StrataScratch, LeetCode SQL | ⬜
📝 WEEKLY ASSIGNMENT: Load S3 data into Redshift, run analytical queries, explain distribution
📌 WEEK 8 — CloudWatch, EC2 & VPC Basics
🎯 Weekly Goal: Monitor a Lambda/Glue job with CloudWatch. Set up alerts
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 50 (Mon) | CloudWatch Logs | Log groups, log streams, log insights queries. View Lambda logs | Query Lambda CloudWatch logs: find all ERROR lines in last 1 hour | AWS CloudWatch docs | ⬜
Day 51 (Tue) | CloudWatch Metrics | Metrics, dashboards, alarms. Create alarm on Lambda error count | Create CloudWatch alarm: if Lambda errors > 3 in 5 min, send SNS email | AWS CloudWatch alarms | ⬜
Day 52 (Wed) | EC2 Basics | Launch EC2 instance (t2.micro). SSH, key pairs, security groups, AMI | Launch EC2, SSH in, install Python, run your ETL script from Month 1 | AWS EC2 getting started | ⬜
Day 53 (Thu) | VPC Basics | VPC, subnets (public/private), internet gateway, NAT gateway, security groups | Draw VPC architecture. Identify default VPC components in your account | AWS VPC docs | ⬜
Day 54 (Fri) | Networking for DE | How Redshift, Glue, Lambda connect in VPC. Security group rules | Configure security group to allow Redshift access only from specific IP | AWS networking docs | ⬜
Day 55 (Sat) | Error Handling Patterns | Retry logic in Python, Dead Letter Queues (SQS), Lambda destinations | Add try/except + retry to Lambda. Set up DLQ on failed Lambda invocations | AWS Lambda error handling | ⬜
Day 56 (Sun) | Month 2 Project | Full automated pipeline with monitoring | Build: scheduled EventBridge → Lambda → Glue → Redshift → CloudWatch alert | GitHub + AWS | ⬜
📝 WEEKLY ASSIGNMENT: Monitor a Lambda/Glue job with CloudWatch. Set up alerts

## 📅 Month 3 - DE Concepts
📅 MONTH 3: ETL/ELT • STAR SCHEMA • ADVANCED SQL • STEP FUNCTIONS
📌 WEEK 9 — Data Engineering Concepts — ETL, Data Lake, Warehouse
🎯 Weekly Goal: Explain ETL vs ELT, Data Lake vs DWH verbally + write concept doc
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 57 (Mon) | ETL vs ELT | ETL: transform before load. ELT: load raw, transform in warehouse. When to use | Write 1-page comparison: ETL vs ELT with real-world AWS examples | Fundamentals of DE | ⬜
Day 58 (Tue) | Data Lake Concepts | Raw/refined/curated zones. S3 as data lake. File formats: CSV, JSON, Parquet, ORC | Design 3-zone data lake on S3 for an e-commerce company. Draw diagram | AWS Data Lake guide | ⬜
Day 59 (Wed) | Data Warehouse | DWH principles, OLAP vs OLTP, columnar storage benefits, data modeling | List 5 differences between OLTP and OLAP. When would you use Redshift vs RDS? | Kimball Group | ⬜
Day 60 (Thu) | Star Schema | Fact tables, dimension tables, star schema design. Primary/foreign keys | Design star schema for retail: fact_sales + dim_customer, dim_product, dim_date | Kimball Data Warehouse Toolkit | ⬜
Day 61 (Fri) | Snowflake Schema | Snowflake vs star. Normalized dimensions. Trade-offs in query performance | Convert your star schema to snowflake schema. Pros/cons for your use case | Kimball Group | ⬜
Day 62 (Sat) | Partitioning + Data Skew | What is partitioning? Hive partitioning in S3. Data skew problems + solutions | Create partitioned S3 folder structure. Identify skew in a dataset | AWS Glue + Redshift docs | ⬜
Day 63 (Sun) | Batch vs Streaming | Batch processing: scheduled jobs. Streaming: real-time. Micro-batch. Lambda architecture | Create diagram: Lambda architecture for an e-commerce event pipeline | Martin Kleppmann book | ⬜
📝 WEEKLY ASSIGNMENT: Explain ETL vs ELT, Data Lake vs DWH verbally + write concept doc
📌 WEEK 10 — Advanced SQL for Interviews
🎯 Weekly Goal: Solve 20 SQL interview questions from StrataScratch / LeetCode
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 64 (Mon) | SQL Window Functions | ROW_NUMBER, RANK, DENSE_RANK, NTILE. PARTITION BY vs GROUP BY | StrataScratch: Top 5 customers per region using DENSE_RANK | StrataScratch | ⬜
Day 65 (Tue) | LAG/LEAD + Running Total | LAG(), LEAD() for time series. SUM OVER() for running totals | 7-day rolling average of daily sales. Month-over-month growth % | Mode Analytics SQL | ⬜
Day 66 (Wed) | CTEs + Recursion | Recursive CTEs for hierarchies. Multiple CTE chaining | Org hierarchy using recursive CTE. Identify managers with all reports | LeetCode SQL Hard | ⬜
Day 67 (Thu) | SQL Optimization | EXPLAIN plan, push filters down, avoid functions on indexed cols, JOIN order | Take 3 slow queries. Optimize each. Show before/after EXPLAIN plans | Use The Index Luke | ⬜
Day 68 (Fri) | Interview SQL Practice | Common patterns: gaps in data, consecutive days, deduplication, pivots | Solve 10 medium/hard SQL questions on LeetCode or StrataScratch | LeetCode, StrataScratch | ⬜
Day 69 (Sat) | Redshift Advanced SQL | LISTAGG, PIVOT, Redshift-specific functions, system tables (STL_, STV_) | Query STL_QUERY to find top 10 slowest queries in Redshift today | Redshift SQL reference | ⬜
Day 70 (Sun) | SQL Review | Flashcard review all SQL concepts. Timed SQL challenges | 5 timed SQL challenges (20 min each). Document your solutions | HackerRank SQL | ⬜
📝 WEEKLY ASSIGNMENT: Solve 20 SQL interview questions from StrataScratch / LeetCode
📌 WEEK 11 — AWS Step Functions + Advanced Glue
🎯 Weekly Goal: Build multi-step workflow with Step Functions orchestrating Glue + Lambda
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 71 (Mon) | Step Functions Intro | AWS Step Functions: state machine, states (Task, Choice, Wait, Parallel) | Create simple Step Functions state machine: 2 Lambda tasks in sequence | AWS Step Functions docs | ⬜
Day 72 (Tue) | Step Functions + Glue | Orchestrate Glue job from Step Functions. Handle success/failure states | State machine: start Glue job → wait → check status → send SNS on success/fail | AWS Step Functions + Glue integration | ⬜
Day 73 (Wed) | Advanced Glue Patterns | Glue incremental loads, job bookmarks, DynamicFrame vs DataFrame | Implement incremental load using Glue job bookmarks on daily log files | AWS Glue dev guide | ⬜
Day 74 (Thu) | Data Quality Concepts | Null checks, uniqueness, referential integrity, AWS Glue Data Quality | Add data quality checks to Glue job: assert no nulls in key columns | AWS Glue Data Quality docs | ⬜
Day 75 (Fri) | Schema Evolution | Adding/removing columns, schema registry, backward/forward compatibility | Handle new column in S3 CSV without breaking existing Glue job | AWS Glue Schema Registry | ⬜
Day 76 (Sat) | Change Data Capture | CDC concepts: full load vs incremental. CDC with DMS, Debezium overview | Design CDC pipeline: MySQL → DMS → S3 → Glue. Draw architecture | AWS DMS docs | ⬜
Day 77 (Sun) | Concept Revision | Review all data engineering concepts from weeks 9-11 | Create flashcard deck: 30 DE interview concepts with definitions | Anki / Notion | ⬜
📝 WEEKLY ASSIGNMENT: Build multi-step workflow with Step Functions orchestrating Glue + Lambda
📌 WEEK 12 — Month 3 Project + Review
🎯 Weekly Goal: Complete end-to-end data pipeline with star schema and Step Functions
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 78 (Mon) | Project Planning | Design capstone: e-commerce data pipeline architecture on paper | Finalize design: S3 → Glue → Redshift star schema → Athena reports | Draw.io | ⬜
Day 79 (Tue) | Project: S3 Layer | Set up raw/refined/curated S3 structure. Upload sample e-commerce data | Create 3 S3 buckets/prefixes. Upload customers, orders, products CSVs | AWS Console | ⬜
Day 80 (Wed) | Project: Glue ETL | Write Glue job: clean raw data, create fact_sales, join dimensions | Full PySpark Glue job: raw CSVs → star schema DataFrames → Parquet | Glue Studio | ⬜
Day 81 (Thu) | Project: Redshift Load | Load Parquet files to Redshift. Create fact + dimension tables | COPY all Parquet files to Redshift. Run 5 analytical queries | Redshift console | ⬜
Day 82 (Fri) | Project: Orchestration | Wrap everything in Step Functions. Add error handling states | State machine: Glue job → check → Redshift load Lambda → success notification | Step Functions console | ⬜
Day 83 (Sat) | Project: Monitoring | CloudWatch dashboard for the pipeline. Alarm on failures | Create dashboard: Glue job duration, Lambda invocations, Redshift query time | CloudWatch | ⬜
Day 84 (Sun) | Project: Document & Push | Write README, architecture diagram, push all code to GitHub | GitHub repo with README, architecture PNG, all scripts documented | GitHub | ⬜
📝 WEEKLY ASSIGNMENT: Complete end-to-end data pipeline with star schema and Step Functions

## 📅 Month 4 - PySpark
📅 MONTH 4: SPARK ARCHITECTURE • PYSPARK • PARTITIONING • PERFORMANCE
📌 WEEK 13 — Spark Architecture + PySpark Basics
🎯 Weekly Goal: Run PySpark locally and in Glue. Read/write S3 data with PySpark
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 85 (Mon) | Big Data Concepts | Why Hadoop/Spark? Distributed computing, HDFS, MapReduce basics | Read "Big Data is Dead" article. Write: when do you NEED Spark vs Pandas? | Martin Kleppmann blog | ⬜
Day 86 (Tue) | Spark Architecture | Driver, executors, cluster manager, DAG, transformations vs actions | Draw Spark architecture diagram. Explain lazy evaluation with example | Spark docs | ⬜
Day 87 (Wed) | PySpark Setup | Install PySpark locally (pip install pyspark). SparkSession, SparkContext | Create SparkSession. Read CSV. Print schema. Show first 10 rows | PySpark docs | ⬜
Day 88 (Thu) | PySpark DataFrames | select, filter, withColumn, groupBy, agg, orderBy, join in PySpark | Load orders data. Group by customer. Sum revenue. Join with customers | PySpark DataFrame API | ⬜
Day 89 (Fri) | PySpark SQL | spark.sql(), createOrReplaceTempView, SQL queries on DataFrames | Register DF as temp view. Write SQL window function query in PySpark | PySpark SQL docs | ⬜
Day 90 (Sat) | PySpark in Glue | Use PySpark in AWS Glue jobs. DynamicFrame → DataFrame conversion | Convert Glue DynamicFrame to Spark DataFrame. Apply transformations | AWS Glue PySpark docs | ⬜
Day 91 (Sun) | Review + Practice | PySpark exercises on Kaggle dataset | 5 PySpark transformations on NYC taxi data. Push to GitHub | Kaggle | ⬜
📝 WEEKLY ASSIGNMENT: Run PySpark locally and in Glue. Read/write S3 data with PySpark
📌 WEEK 14 — PySpark Performance + Partitioning
🎯 Weekly Goal: Optimize a slow PySpark job: repartition, cache, avoid shuffle
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 92 (Mon) | Partitioning Basics | Default partitions, repartition() vs coalesce(), partition by column | Check default partitions. Repartition orders by year. Compare job plans | PySpark docs | ⬜
Day 93 (Tue) | Data Skew | Skewed partitions: one partition much larger. Salting technique, AQE | Identify skewed column. Apply salting technique. Compare execution time | Databricks blog | ⬜
Day 94 (Wed) | Caching + Persistence | cache(), persist(), storage levels (MEMORY_ONLY, MEMORY_AND_DISK) | Cache a DF used multiple times. Compare job time with/without cache | PySpark docs | ⬜
Day 95 (Thu) | Broadcast Joins | Broadcast small tables to avoid shuffle. broadcast() hint in PySpark | Apply broadcast join when joining large fact table with small dim table | PySpark broadcast docs | ⬜
Day 96 (Fri) | File Formats | Parquet vs ORC vs Avro vs Delta. Columnar benefits. Row group size | Write same data as CSV, Parquet, ORC. Compare file size and query speed | Databricks docs | ⬜
Day 97 (Sat) | Spark UI | Spark Web UI: stages, tasks, shuffle read/write, skew detection | Run a job. Open Spark UI. Find the slowest stage. Identify shuffle | Spark UI docs | ⬜
Day 98 (Sun) | Perf Tuning Project | Take a slow Glue/PySpark job. Apply all optimizations learned | Before/after benchmark: optimize job reducing runtime by 30%+ | AWS Glue + PySpark docs | ⬜
📝 WEEKLY ASSIGNMENT: Optimize a slow PySpark job: repartition, cache, avoid shuffle
📌 WEEK 15 — PySpark Advanced + Large File Handling
🎯 Weekly Goal: Process 1GB+ dataset end-to-end using optimized PySpark in Glue
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 99 (Mon) | UDFs in PySpark | User Defined Functions, pandas_udf (vectorized), when to avoid UDFs | Write UDF to categorize order value (low/mid/high). Compare UDF vs when() | PySpark UDF docs | ⬜
Day 100 (Tue) | Handling Large Files | Reading large CSVs, partitioned Parquet, pushdown predicates, column pruning | Load 500MB+ dataset. Apply predicate pushdown. Check files scanned vs read | PySpark + Parquet docs | ⬜
Day 101 (Wed) | Delta Lake Intro | What is Delta Lake? ACID transactions, time travel, schema enforcement | Write PySpark DataFrame as Delta table. Read older version (time travel) | Delta Lake docs | ⬜
Day 102 (Thu) | Streaming Basics (Spark) | Structured Streaming: readStream, writeStream, triggers, output modes | Read from file stream folder. Transform. Write to output folder | PySpark Structured Streaming | ⬜
Day 103 (Fri) | PySpark Interview Qs | Common PySpark interview: transformations vs actions, shuffle, lazy eval | Answer 15 PySpark interview questions without looking at notes | Glassdoor, InterviewBit | ⬜
Day 104 (Sat) | PySpark on AWS EMR | Overview of EMR: managed Spark/Hadoop. EMR vs Glue decision matrix | Read EMR getting started. Understand when to use EMR over Glue | AWS EMR docs | ⬜
Day 105 (Sun) | PySpark Review | Full PySpark concept review. Flashcards | Create 20 PySpark concept flashcards. Quiz yourself. Time 10 problems | Anki / Notion | ⬜
📝 WEEKLY ASSIGNMENT: Process 1GB+ dataset end-to-end using optimized PySpark in Glue
📌 WEEK 16 — Month 4 Project + Big Data Review
🎯 Weekly Goal: Process large dataset with PySpark + Glue with full optimization
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 106 (Mon) | Project Design | Design big data project: large dataset (GitHub/Kaggle 1GB+) processing | Choose dataset. Plan: schema, transformations, output format, Glue config | Kaggle datasets | ⬜
Day 107 (Tue) | Data Ingestion | Upload large dataset to S3 in partitioned format | Script to split large CSV → partitioned Parquet by year/month → S3 upload | boto3 + pandas | ⬜
Day 108 (Wed) | PySpark Glue Job | Write optimized Glue PySpark job: broadcast joins, repartition, cache | Full PySpark Glue job with broadcast, predicate pushdown, output as Parquet | AWS Glue | ⬜
Day 109 (Thu) | Performance Analysis | Run job. Analyze Spark UI. Identify bottlenecks. Apply fixes | Document: before vs after optimization. Show Spark UI screenshots | Spark UI | ⬜
Day 110 (Fri) | Redshift External Tables | Redshift Spectrum: query S3 Parquet directly without loading | Create external schema in Redshift Spectrum. Query S3 Parquet via SQL | Redshift Spectrum docs | ⬜
Day 111 (Sat) | Cost Optimization | Glue DPU costs, S3 storage classes, Redshift reserved nodes overview | Estimate monthly cost for your pipeline. Identify 3 ways to reduce cost | AWS Pricing Calculator | ⬜
Day 112 (Sun) | Push to GitHub | Document Month 4 project with README and architecture | Complete GitHub push: code, README, architecture diagram, benchmark results | GitHub | ⬜
📝 WEEKLY ASSIGNMENT: Process large dataset with PySpark + Glue with full optimization

## 📅 Month 5 - Streaming+CDC
📅 MONTH 5: KINESIS • CDC • SCHEMA EVOLUTION • ADVANCED PYTHON • SYSTEM DESIGN
📌 WEEK 17 — Amazon Kinesis — Streaming Data
🎯 Weekly Goal: Build real-time streaming pipeline: producer → Kinesis → Lambda → S3
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 113 (Mon) | Streaming Concepts | Batch vs streaming. Event time vs processing time. Watermarks. At-least-once | Draw: batch pipeline vs streaming pipeline. When is each appropriate? | Martin Kleppmann DDIA | ⬜
Day 114 (Tue) | Kinesis Data Streams | Shards, partition keys, retention, GetRecords, PutRecord, IteratorType | Create Kinesis stream (1 shard). Produce 100 test events via CLI | AWS Kinesis docs | ⬜
Day 115 (Wed) | Kinesis + Lambda | Lambda event source mapping on Kinesis. Batch size, bisect on error | Lambda reads from Kinesis stream. Print each record. Handle errors | AWS Kinesis + Lambda docs | ⬜
Day 116 (Thu) | Kinesis Firehose | Firehose: delivery stream to S3/Redshift. Buffering, compression, format convert | Create Firehose to S3. Send events. Verify Parquet files land in S3 | AWS Firehose docs | ⬜
Day 117 (Fri) | Producer Code | Python boto3 Kinesis producer. Batch puts. Partition key strategy | Python script simulating e-commerce clickstream events to Kinesis stream | boto3 Kinesis docs | ⬜
Day 118 (Sat) | Kinesis Analytics | Kinesis Data Analytics (Flink): SQL on streaming data, tumbling windows | Read Kinesis Analytics overview. Understand windowed aggregations | AWS Kinesis Analytics docs | ⬜
Day 119 (Sun) | Streaming Project | End-to-end: Python producer → Kinesis → Lambda → S3 → Athena query | Build full streaming pipeline. Query landed data in Athena. Document | AWS account | ⬜
📝 WEEKLY ASSIGNMENT: Build real-time streaming pipeline: producer → Kinesis → Lambda → S3
📌 WEEK 18 — CDC, Advanced Concepts & System Design
🎯 Weekly Goal: Design a CDC pipeline + explain schema evolution in mock interview
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 120 (Mon) | CDC Deep Dive | CDC: log-based (Debezium), query-based, triggers. DMS overview. Use cases | Design CDC pipeline: RDS MySQL → DMS → S3 → Glue → Redshift. Draw it | AWS DMS docs | ⬜
Day 121 (Tue) | Schema Evolution | Backward/forward compatibility. Avro schema registry. Handling new columns | Simulate schema change: add nullable column. Ensure Glue job still works | AWS Glue Schema Registry | ⬜
Day 122 (Wed) | Data Lineage | What is data lineage? OpenLineage, AWS DataZone, Glue Data Catalog lineage | Document data lineage for your Month 3 project: source → transform → report | AWS DataZone overview | ⬜
Day 123 (Thu) | System Design: DE | How to answer DE system design: requirements, scale, components, trade-offs | Practice: "Design a real-time dashboard for 1M events/day on AWS" | ByteByteGo, Educative.io | ⬜
Day 124 (Fri) | System Design Practice | Design: data lake, reporting pipeline, streaming analytics, log processing | Practice 2 more system design questions. Time yourself (30 min each) | System Design Primer | ⬜
Day 125 (Sat) | Monitoring Advanced | CloudWatch custom metrics, dashboards, log metric filters, X-Ray tracing | Create custom metric from Lambda logs. Build CloudWatch dashboard for pipeline | AWS CloudWatch docs | ⬜
Day 126 (Sun) | Concept Review Day | Review all concepts: CDC, schema evolution, lineage, streaming, system design | Written quiz: 25 concept questions without notes. Grade yourself | Notion / paper | ⬜
📝 WEEKLY ASSIGNMENT: Design a CDC pipeline + explain schema evolution in mock interview
📌 WEEK 19 — Python Advanced for DE
🎯 Weekly Goal: Write production-quality Python ETL with logging, retry, config files
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 127 (Mon) | Python Logging | logging module, log levels, handlers, formatters, structured logging (JSON) | Add proper logging to your ETL scripts: INFO, WARNING, ERROR levels | Python logging docs | ⬜
Day 128 (Tue) | Python Config Files | config.ini, .env, configparser, python-dotenv. Never hardcode credentials | Refactor Month 1 ETL: move all config to .env file. Load in Python | python-dotenv docs | ⬜
Day 129 (Wed) | Python Retry Patterns | tenacity library, exponential backoff, retry decorators, idempotency | Add retry logic to boto3 S3 upload function. Test with forced failure | tenacity docs | ⬜
Day 130 (Thu) | Python OOP for DE | Classes, inheritance, dataclasses. ETL class with extract/transform/load methods | Refactor ETL as Python class with methods: extract(), transform(), load() | Real Python OOP guide | ⬜
Day 131 (Fri) | Unit Testing | pytest, test ETL functions, mock boto3 with moto, test coverage | Write 10 pytest tests for your ETL functions. Mock S3 calls with moto | pytest docs, moto docs | ⬜
Day 132 (Sat) | Python Performance | profiling (cProfile), generators, itertools, vectorized ops vs loops | Profile your ETL. Identify slowest function. Optimize by 50%+ | Python profiling docs | ⬜
Day 133 (Sun) | Python Review | Review all Python concepts. LeetCode 5 medium problems | Solve 5 LeetCode mediums in Python. Focus on arrays, strings, dicts | LeetCode | ⬜
📝 WEEKLY ASSIGNMENT: Write production-quality Python ETL with logging, retry, config files
📌 WEEK 20 — Month 5 Project + Pre-Interview Prep
🎯 Weekly Goal: Complete streaming pipeline project + start mock interview practice
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 134 (Mon) | Streaming Project | Build production-grade streaming pipeline with all best practices | E-commerce clickstream: Kinesis → Lambda (with logging/retry) → S3 Parquet | AWS account | ⬜
Day 135 (Tue) | Mock Interview 1 | Data Engineering concepts interview (60 min timed) | Ask ChatGPT to interview you on DE concepts. Record your answers | ChatGPT / Pramp | ⬜
Day 136 (Wed) | Mock Interview 2 | SQL interview round (60 min, 5 questions hard level) | 5 LeetCode hard SQL questions. Time 12 min each. Review solutions | LeetCode | ⬜
Day 137 (Thu) | Mock Interview 3 | Python coding round (45 min, 2 medium problems) | 2 LeetCode medium Python. Focus on clean code and explain while typing | LeetCode | ⬜
Day 138 (Fri) | Portfolio Review | Review all GitHub projects. Write clear READMEs for all 4 projects | Polish all 4 month projects. Add screenshots, architecture diagrams | GitHub | ⬜
Day 139 (Sat) | Resume Update | Update resume with new AWS skills, projects, certifications if any | Update resume: add AWS projects with impact metrics. Have someone review | Resume templates | ⬜
Day 140 (Sun) | Weak Areas Review | Identify your top 5 weak areas. Study each for 45 min | Targeted study on 3 weakest topics identified from mock interviews | All resources | ⬜
📝 WEEKLY ASSIGNMENT: Complete streaming pipeline project + start mock interview practice

## 📅 Month 6 - Interview Prep
📅 MONTH 6: CAPSTONE PROJECTS • 50 MOCK QUESTIONS • SYSTEM DESIGN • JOB APPLICATIONS
📌 WEEK 21 — Capstone Project 1 + Concept Revision
🎯 Weekly Goal: Complete Capstone Project 1 and revise all 8 skill areas
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 141 (Mon) | Capstone 1 Design | Full DE pipeline: batch ingestion + CDC + star schema + Redshift + monitoring | Design architecture for "Retail Analytics Platform" on AWS. Full diagram | Draw.io | ⬜
Day 142 (Tue) | Capstone 1 Build: Ingestion | S3 data lake setup, Glue crawlers, raw → refined → curated zones | Upload retail data. Configure crawlers. Catalog all tables | AWS Glue | ⬜
Day 143 (Wed) | Capstone 1 Build: ETL | PySpark Glue job: clean, join, aggregate. Star schema creation | Glue PySpark: raw data → fact_sales + 3 dim tables as Parquet in S3 | AWS Glue Studio | ⬜
Day 144 (Thu) | Capstone 1 Build: DWH | Load to Redshift, create views, analytical queries, Redshift Spectrum | COPY to Redshift. Create 5 analytical views. Spectrum query for history | Redshift | ⬜
Day 145 (Fri) | Capstone 1 Build: Orchestration | Step Functions for full pipeline. Alerts on failure | State machine: crawl → Glue → Redshift load → success/fail notification | Step Functions | ⬜
Day 146 (Sat) | Capstone 1 Documentation | Full README, architecture diagram, setup instructions, sample queries | Push to GitHub with complete documentation. Add to resume | GitHub | ⬜
Day 147 (Sun) | Concept Revision Day | Full revision: ETL/ELT, star schema, partitioning, CDC, streaming | Verbal explanation of all 30 DE concepts. Record yourself (5 min video) | Your notes | ⬜
📝 WEEKLY ASSIGNMENT: Complete Capstone Project 1 and revise all 8 skill areas
📌 WEEK 22 — Capstone Project 2 + Advanced Interview Prep
🎯 Weekly Goal: Complete real-time streaming project + answer 50 interview questions
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 148 (Mon) | Capstone 2 Design | Real-time streaming: IoT sensor data → Kinesis → Lambda → S3 → Dashboard | Design IoT analytics platform. Define SLA: < 5 sec latency, 99.9% uptime | Draw.io | ⬜
Day 149 (Tue) | Capstone 2: Producer | Python producer simulating IoT sensor events at 1000 events/sec | IoT producer with threading. Send to Kinesis stream with proper partitioning | Python + boto3 | ⬜
Day 150 (Wed) | Capstone 2: Processing | Lambda consumer with aggregations. Firehose to S3 as Parquet | Lambda: 1-min window aggregations → write to DynamoDB. Firehose → S3 | AWS Lambda + Firehose | ⬜
Day 151 (Thu) | Capstone 2: Analytics | Athena queries on S3. CloudWatch dashboard for real-time metrics | Athena queries on sensor data. Dashboard: events/sec, anomaly counts | Athena + CloudWatch | ⬜
Day 152 (Fri) | Interview: 50 Questions | Answer 50 technical interview questions across all topics | 50 Q&A: 15 AWS, 10 SQL, 5 Python, 10 DE concepts, 5 PySpark, 5 system design | InterviewBit, Glassdoor | ⬜
Day 153 (Sat) | Capstone 2 Documentation | Full README, architecture, performance benchmarks, push to GitHub | Complete GitHub for Capstone 2. Add to LinkedIn and resume | GitHub | ⬜
Day 154 (Sun) | Mock Technical Screen | Full 90-min mock technical interview with all areas covered | Pramp.com or ask friend: 45 min SQL + coding, 45 min DE concepts + system design | Pramp.com | ⬜
📝 WEEKLY ASSIGNMENT: Complete real-time streaming project + answer 50 interview questions
📌 WEEK 23 — Interview Mastery Week
🎯 Weekly Goal: Pass 3 mock interviews with 80%+ score + finalize job applications
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 155 (Mon) | Behavioral Round Prep | STAR method: Situation, Task, Action, Result. Common DE behavioral Qs | Write 10 STAR stories: conflict, failure, optimization, leadership, delivery | STAR method guide | ⬜
Day 156 (Tue) | System Design Round | Practice 3 full system design Qs with timing (30 min each) | Design: "Twitter firehose", "Netflix recommendation data pipeline", "Uber surge" | ByteByteGo | ⬜
Day 157 (Wed) | Redshift Deep Dive | Advanced Redshift: WLM, concurrency scaling, RA3, Serverless Redshift | Read Redshift WLM docs. Explain: how would you handle 50 concurrent queries? | AWS Redshift advanced docs | ⬜
Day 158 (Thu) | SQL Final Practice | 10 hard SQL questions from FAANG-style interviews. 12 min each | 10 LeetCode Hard SQL. Review every answer. Note patterns | LeetCode Hard SQL | ⬜
Day 159 (Fri) | Mock Interview 4 | Full DE mock: 30 min concept Qs + 30 min SQL + 30 min system design | Record mock interview. Review playback. Note top 3 improvements | Pramp / Interviewing.io | ⬜
Day 160 (Sat) | Mock Interview 5 | Another full mock with different interviewer or topic set | Focus weak areas from Mock 4. Aim for 85%+ score | Pramp / friend | ⬜
Day 161 (Sun) | Job Application Blitz | Apply to 20+ AWS Data Engineer roles. LinkedIn optimization | Apply: Naukri, LinkedIn, AngelList. Customize resume for each role | Naukri, LinkedIn | ⬜
📝 WEEKLY ASSIGNMENT: Pass 3 mock interviews with 80%+ score + finalize job applications
📌 WEEK 24 — Final Stretch — Applications & Continuous Improvement
🎯 Weekly Goal: Land first ₹20 LPA AWS Data Engineer interview offer!
Day | Topic | What to Study / Learn | Practice Task | Resources | ✅ Done?
Day 162 (Mon) | AWS Certification Plan | AWS Certified Data Engineer Associate or Cloud Practitioner overview | Read exam guide. Plan 2-week study for AWS CDE exam post-job search | AWS Training | ⬜
Day 163 (Tue) | Networking | LinkedIn outreach to 10 AWS Data Engineers in India. Ask for referrals | Send personalized connection requests. Engage with DE content on LinkedIn | LinkedIn | ⬜
Day 164 (Wed) | Company Research | Research target companies: tech stack, culture, interview process | Shortlist 10 target companies. Read Glassdoor reviews. Note DE team stack | Glassdoor, LinkedIn | ⬜
Day 165 (Thu) | Final SQL Grind | Last SQL practice: focus on medium/hard patterns, time yourself | 15 SQL problems in 3 hours. Mixed: window functions, CTEs, optimization | LeetCode | ⬜
Day 166 (Fri) | Final Python Grind | Last Python practice: ETL patterns, data manipulation, clean code | 10 Python problems: file I/O, pandas, OOP, exception handling | LeetCode | ⬜
Day 167 (Sat) | Final DE Concept Quiz | 50-question final quiz covering all 6 months of content | Timed 50 Q quiz: all concepts, no notes. Score 40+ to call yourself ready! | Your notes / Anki | ⬜
Day 168 (Sun) | 🎉 Day 168 — READY! | Celebrate! You've completed 6 months of intense AWS DE preparation | Final checklist: 2 GitHub projects, SQL strong, AWS proficient, resume polished! | Go get that ₹20 LPA job! 🚀 | ⬜
📝 WEEKLY ASSIGNMENT: Land first ₹20 LPA AWS Data Engineer interview offer!

## 🔢 SQL Skills
🔢 SQL MASTERY — ALL TOPICS (Basic → Advanced, Interview-Ready)
# | Skill / Topic | What to Learn | Practice Exercise | Resources | Done?
1 | SELECT Basics | SELECT, WHERE, ORDER BY, LIMIT, DISTINCT, aliasing columns and tables | Write 10 basic SELECT queries on Northwind DB | SQLZoo, W3Schools | ⬜
2 | JOINs (All Types) | INNER, LEFT, RIGHT, FULL OUTER, CROSS, SELF JOIN. Know when to use each | Find customers with no orders using LEFT JOIN + IS NULL | Mode Analytics SQL Tutorial | ⬜
3 | GROUP BY + HAVING | Aggregate functions: COUNT, SUM, AVG, MIN, MAX. Filter groups with HAVING | Monthly revenue by product category. Filter categories with revenue > 10K | StrataScratch | ⬜
4 | CASE WHEN | Conditional logic in SQL. CASE in SELECT, GROUP BY, ORDER BY | Classify orders as low/mid/high value. Pivot using CASE WHEN | LeetCode SQL | ⬜
5 | Subqueries | Subquery in WHERE, FROM, SELECT. Correlated vs uncorrelated subqueries | Employees earning more than dept average (correlated subquery) | StrataScratch, LeetCode | ⬜
6 | CTEs (WITH clause) | Common Table Expressions. Multiple CTEs. Recursive CTEs for hierarchies | Find 2nd highest salary per dept using CTE. Org hierarchy with recursive CTE | LeetCode Hard SQL | ⬜
7 | Window Functions | ROW_NUMBER, RANK, DENSE_RANK, NTILE, FIRST_VALUE, LAST_VALUE | Top 3 customers per region. Assign quartile to products by revenue | Mode Analytics, StrataScratch | ⬜
8 | LAG / LEAD | Compare current row to previous/next row. Great for time series analysis | 7-day rolling average sales. Month-over-month growth rate using LAG() | StrataScratch | ⬜
9 | Running Totals | SUM(...) OVER (ORDER BY ...) for running/cumulative aggregations | Cumulative revenue by date. Running total of daily signups | Mode Analytics | ⬜
10 | Indexing Basics | B-tree indexes, clustered vs non-clustered, composite index, when indexes help | Create index on order_date. Run EXPLAIN before/after. Explain the difference | Use The Index Luke | ⬜
11 | Query Optimization | EXPLAIN / EXPLAIN ANALYZE, filter early, avoid SELECT *, avoid functions on indexed cols | Find slow query in your DB. Optimize it. Show EXPLAIN plan improvement | Use The Index Luke | ⬜
12 | Performance Tuning | Query plan analysis, statistics, vacuum/analyze (Postgres), materialized views | Create materialized view for monthly summary. Compare query time | PostgreSQL docs | ⬜
13 | Redshift SQL | Redshift-specific: DISTKEY, SORTKEY, system tables (STL_, STV_), WLM | Query STL_QUERY for slowest queries. Check table distribution skew | AWS Redshift docs | ⬜
14 | SQL Interview Patterns | Deduplication, gaps and islands, pivots, median, nth highest, consecutive days | Solve 20 LeetCode SQL Medium/Hard problems. Note patterns | LeetCode SQL Hard list | ⬜

## 🐍 Python Skills
🐍 PYTHON MASTERY — ALL TOPICS FOR DATA ENGINEERING
# | Skill / Topic | What to Learn | Practice Exercise | Resources | Done?
1 | Variables & Data Types | int, str, float, bool, list, dict, tuple, set. Type casting | Build a simple calculator. Store results in dict | Python.org docs | ⬜
2 | Control Flow | if/elif/else, for, while, break, continue, pass, range() | FizzBuzz, find primes up to 100, reverse a list without built-in | W3Schools Python | ⬜
3 | Functions | def, return, *args, **kwargs, lambda, default args, docstrings | Write 10 utility functions: is_palindrome, find_duplicates, flatten_list | Real Python | ⬜
4 | File Handling | open(), read, write, append, with statement, CSV module, JSON | Read CSV → filter → write to new CSV. Read/write JSON config file | Python docs | ⬜
5 | Exception Handling | try/except/else/finally, raise, custom exceptions, Exception hierarchy | Wrap all file/network operations in try/except. Log specific errors | Python docs | ⬜
6 | Pandas - Basics | read_csv, head, info, describe, shape, dtypes, rename, drop | Load 3 CSVs from Kaggle. Explore each dataset thoroughly | Pandas docs | ⬜
7 | Pandas - Transform | filter, groupby, merge, pivot_table, apply, map, fillna, dropna | Sales analysis: group by region, pivot by month, merge customer info | Pandas 10 min tutorial | ⬜
8 | Pandas - ETL Patterns | Chaining operations, efficient transforms, reading large files in chunks | Process 500MB CSV in chunks. Apply transformations. Output Parquet | Pandas docs | ⬜
9 | boto3 - S3 | put_object, get_object, list_objects_v2, delete_object, copy_object | Upload, list, download, delete files in S3 with boto3 | boto3 S3 docs | ⬜
10 | boto3 - Glue/Lambda | start_job_run, get_job_run, invoke Lambda, describe functions | Start Glue job from Python. Poll job status until completion | boto3 Glue/Lambda docs | ⬜
11 | Logging Module | logging levels, handlers, formatters, structured logging (JSON), logging config | Add logging to ETL: INFO for progress, ERROR for failures, WARNING for data issues | Python logging HOWTO | ⬜
12 | Config & Env Vars | os.environ, dotenv, configparser, never hardcode secrets | Move all config (bucket names, DB creds) to .env. Load with dotenv | python-dotenv docs | ⬜
13 | Retry Patterns | tenacity, exponential backoff, max attempts, retry conditions | Add retry decorator to S3 upload and Glue job status check functions | tenacity docs | ⬜
14 | OOP for ETL | Classes, __init__, methods, inheritance, dataclasses, @staticmethod | Refactor ETL as ETLPipeline class with extract(), transform(), load() methods | Real Python OOP | ⬜
15 | Unit Testing | pytest, assert, fixtures, mocking with unittest.mock, moto for AWS | Write 15 tests for your ETL functions. Mock all AWS calls | pytest docs + moto docs | ⬜

## ☁️ AWS Skills
☁️ AWS DATA ENGINEERING SERVICES — ALL TOPICS
# | Skill / Topic | What to Learn | Practice Exercise | Resources | Done?
1 | IAM Users & Groups | Create users, assign to groups, attach managed policies, principle of least privilege | Create IAM user with only S3 read access. Test by trying to upload (should fail) | AWS IAM docs | ⬜
2 | IAM Roles & Policies | Role trust policy, permission policy, JSON structure, policy simulator | Write custom policy allowing Lambda to read specific S3 bucket and log to CW | AWS Policy Simulator | ⬜
3 | S3 Fundamentals | Buckets, objects, keys, presigned URLs, versioning, MFA delete | Enable versioning. Upload, update, view version history, restore old version | AWS S3 docs | ⬜
4 | S3 Lifecycle Rules | Transition to IA, Glacier, Intelligent-Tiering. Expiration rules | Create lifecycle: move to IA after 30 days, Glacier after 90, delete after 365 | AWS S3 lifecycle docs | ⬜
5 | S3 Partitioned Data | Hive-style partitioning: s3://bucket/year=2024/month=01/. Benefits for Athena | Upload data to partitioned S3 path. Query with Athena using partition filtering | AWS Athena partitions | ⬜
6 | AWS Glue Crawlers | Configure crawler: IAM role, data store, database, schedule, classifiers | Run crawler on partitioned S3 data. Verify schema and partitions in catalog | AWS Glue docs | ⬜
7 | AWS Glue Jobs | Glue ETL job: script, DPUs, triggers, job bookmarks, monitoring | Create Glue job. Transform data. Enable bookmark. Run twice: verify idempotency | AWS Glue Studio | ⬜
8 | Amazon Redshift | Cluster setup, table design (DISTKEY/SORTKEY), COPY command, VACUUM/ANALYZE | Create cluster. Load S3 Parquet. Run EXPLAIN on 3 queries. Add sort key | AWS Redshift docs | ⬜
9 | AWS Lambda | Function, handler, runtime, memory/timeout, triggers, environment vars, layers | Lambda triggered by S3: read uploaded file, transform, write to another S3 | AWS Lambda docs | ⬜
10 | Amazon EventBridge | Rules, event patterns, cron schedules, targets (Lambda, Step Functions) | Schedule Lambda daily at 8 AM. Create custom event rule for business events | AWS EventBridge docs | ⬜
11 | AWS Step Functions | State machine, states, transitions, error handling, retry, wait for callback | Build 4-state machine: Glue → check status → Redshift load → notify | AWS Step Functions docs | ⬜
12 | Amazon Kinesis | Data Streams vs Firehose. Shards, partition keys, delivery to S3/Redshift | Stream mock events to Kinesis. Firehose delivers Parquet to S3 | AWS Kinesis docs | ⬜
13 | Amazon CloudWatch | Log groups/streams, metrics, alarms, dashboards, Logs Insights | Create alarm on Lambda errors. Build dashboard for pipeline health | AWS CloudWatch docs | ⬜
14 | EC2 Basics | Instance types, AMI, key pairs, security groups, SSH access, user data | Launch t2.micro, SSH in, install Python, run ETL script | AWS EC2 docs | ⬜
15 | VPC Basics | VPC, public/private subnets, internet gateway, NAT gateway, security groups | Draw default VPC architecture. Understand how Redshift connects to Glue | AWS VPC docs | ⬜

## ⚡ PySpark Skills
⚡ PYSPARK & BIG DATA — ALL TOPICS FOR AWS DATA ENGINEER
# | Skill / Topic | What to Learn | Practice Exercise | Resources | Done?
1 | Spark Architecture | Driver, executors, cluster manager (YARN/Kubernetes/Standalone), master node | Draw Spark cluster diagram. Explain how a job flows from driver to executors | Spark docs | ⬜
2 | Lazy Evaluation | Transformations (lazy) vs actions (trigger execution). DAG creation | Create a chain of 5 transformations. Explain when execution actually happens | Spark docs | ⬜
3 | SparkSession Setup | SparkSession.builder, appName, config, getOrCreate. Local vs cluster mode | Start SparkSession in local[2] mode. Read a CSV. Show schema | PySpark docs | ⬜
4 | DataFrame Operations | select, filter, where, withColumn, drop, rename, cast, distinct | Load customer data. Select key columns. Filter active users. Rename columns | PySpark API docs | ⬜
5 | Aggregations | groupBy, agg, count, sum, avg, max, min, pivot, rollup, cube | Sales by region and product. Pivot months as columns. Rollup for subtotals | PySpark docs | ⬜
6 | Joins in PySpark | inner, left, right, full, semi, anti joins. Avoiding shuffle with broadcast | Join orders (large) with products (small). Apply broadcast hint. Check Spark UI | PySpark join docs | ⬜
7 | PySpark SQL | createOrReplaceTempView, spark.sql(), mixing SQL and DataFrame API | Register 3 DataFrames as views. Write complex SQL with window functions | PySpark SQL docs | ⬜
8 | Partitioning | repartition(n), coalesce(n), partitionBy column, default parallelism | Check partitions. Repartition by date. Write partitioned Parquet to S3 | PySpark docs | ⬜
9 | Caching | cache(), persist(), unpersist(), StorageLevel options | Cache a DF used in 3 different aggregations. Measure time with/without | PySpark docs | ⬜
10 | Broadcast Joins | broadcast() function, automatic broadcast threshold, when to use | Force broadcast on lookup table < 100MB. Verify in Spark UI (no shuffle) | PySpark broadcast docs | ⬜
11 | File Formats | Read/write CSV, JSON, Parquet, ORC, Avro, Delta. Compression options | Write same data as CSV vs Parquet. Compare file size and read time | PySpark IO docs | ⬜
12 | UDFs | udf(), pandas_udf(), return types. When UDFs hurt performance | Write UDF to parse custom date format. Compare to built-in to_date() speed | PySpark UDF docs | ⬜
13 | Data Skew | Identifying skewed partitions, salting technique, skew hints, AQE in Spark 3 | Create skewed dataset. Apply salting. Verify uniform partition sizes | Databricks blog on skew | ⬜
14 | Spark UI | Jobs, stages, tasks, shuffle read/write, executor memory, GC time | Run a job. Identify slowest stage. Check shuffle bytes. Find skewed tasks | Spark UI guide | ⬜
15 | PySpark in AWS Glue | Glue DynamicFrame, applyMapping, resolveChoice, datasink, Glue context | Write full Glue PySpark job using GlueContext. Convert to/from DF as needed | AWS Glue PySpark docs | ⬜

## 📚 DE Concepts
📚 DATA ENGINEERING CONCEPTS — INTERVIEW CRITICAL (30 Topics)
# | Skill / Topic | What to Learn | Practice Exercise | Resources | Done?
1 | ETL vs ELT | ETL: transform before load (traditional DWH). ELT: load raw, transform in DWH (cloud-native) | Draw both architectures. Give AWS example of each. Pros/cons for each approach | Fundamentals of DE | ⬜
2 | Data Lake | Raw/refined/curated zones, schema-on-read, S3 as data lake, file formats, governance | Design data lake for an e-commerce company. Assign zones to each data type | AWS Data Lake guide | ⬜
3 | Data Warehouse | Schema-on-write, OLAP, columnar storage, optimized for analytics reads | Compare Redshift vs Snowflake vs BigQuery. When to choose each? | Kimball Group | ⬜
4 | Star Schema | Fact tables (metrics, FKs), dimension tables (attributes), grain definition | Design star schema for retail: fact_sales, dim_customer, dim_product, dim_date | Kimball Data Warehouse Toolkit | ⬜
5 | Snowflake Schema | Normalized dimensions, reduced redundancy, more joins, less storage | Normalize dim_product into dim_product + dim_category + dim_brand | Kimball Group | ⬜
6 | Fact & Dim Tables | Fact types: transactional, periodic snapshot, accumulating snapshot. Dim: SCD types | Classify 10 columns as fact or dimension. Define SCD Type 2 for customer address | Kimball book | ⬜
7 | SCD Types | SCD Type 1 (overwrite), Type 2 (versioned rows), Type 3 (columns). Trade-offs | Implement SCD Type 2 for customer table: add start_date, end_date, is_current | Kimball book | ⬜
8 | Partitioning | Why partition data? Hive partitioning, partition pruning, over-partitioning risks | Design partition strategy for 1TB log data. Estimate cost savings vs no partition | AWS Glue + Athena docs | ⬜
9 | Data Skew | Hot partitions, causes, detection (Spark UI), solutions: salting, AQE, broadcast | Identify skewed column in a dataset. Explain 2 remediation strategies to interviewer | Databricks blog | ⬜
10 | Batch Processing | Scheduled jobs, high throughput, latency-tolerant. Tools: Glue, Spark, Airflow | Design batch pipeline for daily sales summary. Define SLA: complete by 6 AM IST | Fundamentals of DE | ⬜
11 | Streaming | Real-time, event-driven, low latency. Tools: Kinesis, Kafka, Flink, Spark Streaming | Design streaming pipeline for fraud detection. Define acceptable latency | Designing Data-Intensive Apps | ⬜
12 | Schema Evolution | Adding nulls ok, removing cols risky, renaming cols breaking. Schema registry | Test: add nullable column to Glue source. Verify downstream pipeline not broken | AWS Glue Schema Registry | ⬜
13 | Change Data Capture | Log-based (Debezium/DMS), query-based, trigger-based. Full vs incremental load | Design CDC: MySQL → DMS → S3 → Glue → Redshift. Handle deletes and updates | AWS DMS docs | ⬜
14 | Data Quality | Completeness, accuracy, consistency, timeliness, uniqueness. DQ frameworks | Add 5 data quality checks to Glue job: null rate, uniqueness, value range | Great Expectations docs | ⬜
15 | Idempotency | Running a pipeline multiple times = same result. DELETE+INSERT vs UPSERT patterns | Rewrite your ETL to be idempotent: overwrite S3 partition + UPSERT Redshift | Your own ETL code | ⬜

## 📝 Weekly Assignments
📝 ALL 24 WEEKLY ASSIGNMENTS — 6 MONTH PLAN
Wk | Month | Assignment | Deliverable | GitHub? | Status
1 | Month 1 | Python Basics Project | Python script: reads CSV, cleans nulls, groups by category, writes output CSV | Yes | ⬜
2 | Month 1 | Pandas + SQL ETL | Python ETL: load data → pandas transform → SQLite → query with Python | Yes | ⬜
3 | Month 1 | Linux + Git + AWS CLI | AWS CLI: create S3 bucket, sync folder, list objects. All commands in bash script | Yes | ⬜
4 | Month 1 | S3 Python Integration | boto3 ETL: read CSV → Pandas transform → write Parquet to S3 (partitioned) | Yes | ⬜
5 | Month 2 | Glue Crawler + Catalog | Glue crawler on S3 CSV data. Athena query on cataloged table. Screenshot of catalog | Yes | ⬜
6 | Month 2 | Lambda Event Pipeline | S3 upload → Lambda → starts Glue ETL job → CloudWatch logs show success | Yes | ⬜
7 | Month 2 | Redshift Data Load | S3 Parquet → Redshift COPY → 10 analytical SQL queries → screenshot results | Yes | ⬜
8 | Month 2 | Full Automated Pipeline | EventBridge scheduled → Lambda → Glue → Redshift → CloudWatch alarm | Yes | ⬜
9 | Month 3 | ETL/ELT Concept Doc | 2-page document: ETL vs ELT, Data Lake vs DWH with AWS examples and diagrams | Yes | ⬜
10 | Month 3 | Advanced SQL (20 Questions) | 20 medium/hard SQL solutions with explanations on StrataScratch/LeetCode | Yes | ⬜
11 | Month 3 | Step Functions Workflow | State machine: Glue → check status → Lambda Redshift load → SNS notification | Yes | ⬜
12 | Month 3 | Month 3 Capstone | E-commerce pipeline: S3 → Glue PySpark → Redshift star schema → Step Functions | Yes | ⬜
13 | Month 4 | PySpark Local ETL | PySpark job locally: load large CSV, transform, write Parquet. Spark UI screenshot | Yes | ⬜
14 | Month 4 | PySpark Optimization | Before/after benchmark: add broadcast join, repartition, cache. Show 30%+ improvement | Yes | ⬜
15 | Month 4 | PySpark Advanced | Process 500MB+ dataset: predicate pushdown, column pruning, UDFs avoided | Yes | ⬜
16 | Month 4 | Big Data Glue Project | Optimized Glue PySpark job on 1GB+ dataset. Full GitHub documentation + benchmarks | Yes | ⬜
17 | Month 5 | Kinesis Streaming Pipeline | Python producer → Kinesis stream → Lambda → S3 Parquet → Athena query | Yes | ⬜
18 | Month 5 | CDC Architecture Design | CDC design doc: MySQL → DMS → Glue incremental → Redshift UPSERT with diagram | Yes | ⬜
19 | Month 5 | Production-Grade Python ETL | ETL with logging, dotenv config, retry decorator, pytest tests (10 tests), OOP class | Yes | ⬜
20 | Month 5 | 50 Interview Q&A + Mock | 50 written Q&A document + 1 recorded mock interview (90 min). Self-scored rubric | No | ⬜
21 | Month 6 | Capstone 1: Retail Analytics | Full batch pipeline: S3 lake → Glue PySpark → Redshift star schema → Step Functions | Yes | ⬜
22 | Month 6 | Capstone 2: IoT Streaming | Real-time: Python producer → Kinesis → Lambda → Firehose → S3 → CloudWatch dash | Yes | ⬜
23 | Month 6 | 3 Mock Interviews Passed | 3 mock interview recordings. Score 80%+ on all rounds. Written improvement notes | No | ⬜
24 | Month 6 | Job Application Blitz | 20 applications sent. Resume finalized. LinkedIn optimized. Referral outreach done | No | ⬜

## 🔗 Resources
🔗 CURATED RESOURCES FOR AWS DATA ENGINEERING
Category | Resource Name | What You Learn | URL / Location | Free?
Python | Python.org Official Docs | Complete Python language reference and tutorials | https://docs.python.org/3/ | Free ✅
Python | Real Python | Practical Python tutorials for data engineering patterns | https://realpython.com | Free/Paid
Python | Pandas Documentation | Complete Pandas API for data manipulation | https://pandas.pydata.org/docs/ | Free ✅
SQL | SQLZoo | Interactive SQL exercises from beginner to advanced | https://sqlzoo.net | Free ✅
SQL | Mode Analytics SQL Tutorial | Comprehensive SQL guide with real-world examples | https://mode.com/sql-tutorial/ | Free ✅
SQL | StrataScratch | Real interview SQL questions from top companies | https://stratascratch.com | Free/Paid
SQL | LeetCode SQL | SQL problems categorized by company and difficulty | https://leetcode.com/problemset/database/ | Free/Paid
SQL | Use The Index, Luke | Deep dive into SQL performance and indexing | https://use-the-index-luke.com | Free ✅
AWS | AWS Free Tier | Practice all AWS services for free (12 months) | https://aws.amazon.com/free/ | Free ✅
AWS | AWS Documentation | Official docs for all AWS services | https://docs.aws.amazon.com | Free ✅
AWS | AWS Workshops | Hands-on labs for AWS services | https://workshops.aws | Free ✅
AWS | Tutorials Dojo | AWS certification practice exams and cheat sheets | https://tutorialsdojo.com | Free/Paid
PySpark | PySpark Official Docs | Complete PySpark API and programming guide | https://spark.apache.org/docs/latest/api/python/ | Free ✅
PySpark | Databricks Academy | Spark fundamentals free training | https://academy.databricks.com | Free ✅
PySpark | Databricks Blog | Best practices for Spark optimization and Delta Lake | https://databricks.com/blog | Free ✅
DE Concepts | Fundamentals of Data Engineering | Best book for DE concepts (Joe Reis & Matt Housley) | O'Reilly / Amazon | Paid
DE Concepts | Designing Data-Intensive Apps | Deep systems knowledge for data engineers (Kleppmann) | O'Reilly / Amazon | Paid
DE Concepts | The Data Warehouse Toolkit | Kimball methodology: star schema and dimensional modeling | Amazon | Paid
Interview Prep | LeetCode | Coding problems for Python and SQL interview practice | https://leetcode.com | Free/Paid
Interview Prep | Pramp | Free mock technical interviews with real engineers | https://www.pramp.com | Free ✅
Interview Prep | ByteByteGo | System design concepts and visual explanations | https://bytebytego.com | Free/Paid
Interview Prep | InterviewBit | Data engineering and software interview preparation | https://www.interviewbit.com | Free ✅
Jobs India | Naukri.com | India job portal — search "AWS Data Engineer" roles | https://naukri.com | Free ✅
Jobs India | LinkedIn Jobs | Set alert: "Data Engineer" + "AWS" + "Bengaluru" | https://linkedin.com/jobs | Free ✅
Tools | DBeaver Community | Free SQL client for Redshift, PostgreSQL, SQLite | https://dbeaver.io | Free ✅
Tools | Draw.io | Free diagramming for architecture and schema design | https://draw.io | Free ✅